| September 2023 UPDATE |  |  |  |
| --- | --- | --- | --- |
| ## Department Contact: | Jarrod Lyman | ## Date: | 9/8/23 |
| ## Percentage Complete: | 5% | ## Target Completion: | December 2025 |
| ## Goal 3.2 – Community Engagement |  |  |  |

# Important or Relevant Dates/Milestones: (looking ahead at the next 3 months) # Dec 2023 Hire new Community Engagement Specialist

# Status: (What has been done/Is Being Done) # Approval of an FTE for the Community Engagement Specialist came on 9/6. The job was posted the morning of 9/7. Initial timeline hopes to have the replacement on board by December. This person will then take over the liaison roles with YAC and CIC and work within the community to increase usage of the engagement tools on the website.