| September 2023 UPDATE |  |  |  |
| --- | --- | --- | --- |
| ## Department Contact: | Economic Development | ## Date: | September 13, 2023 |
|  | 5% | ## Target Completion: | 06/30/24 |
| ## Goal 5.1 Create and promote a tourism infrastructure that doesn’t negatively impact neighborhoods and supports economic development to promote a healthy, sustainable local economy. |  |  |  |

# Important or Relevant Dates/Milestones: (looking ahead at the next 3 months) # Promote the new 2023/2025 round of available funding for City-Sponsored Public Event Program (October 2023). # Recommend policies and strategies too enable the transferal of tourism activity to a legally organized entity that will serve as a Destination Management Agency (“DMO”) to manage and operate tourism program from outside of City Government.

# Status: (What has been done/Is Being Done) City-Sponsored - Still collecting receipts from the 2021/2023 City-Sponsored Public Events - DOCA’s receipts are still outstanding. - Three River Arts Guild receipts are still outstanding. - OC Brewing Receipts have been received (Sept 2023) - Tweaking existing guidelines to require receipts to be turned in by a specific date or event organizer will forfeit the 20% that was held back to ensure that receipts for all eligible costs are accounted for. Destination Management Organization - Collecting written documentation from other communities that have operated a DMO