| March 2024 UPDATE |  |  |  |
| --- | --- | --- | --- |
| ## Department Contact: | Planning/Public Works | ## Date: | 3/12/2024 |
| ## Percentage Complete: | 40% | ## Timeline: | Ongoing |
| ## Goal 7, Strategy 7.1 - Determine and Establish Relationships with the Tribes that have a Shared History with Oregon City |  |  |  |  |

# Important or Relevant Dates/Milestones: # Continual identification of opportunities to improve communication: # ongoing meetings # Staff continue to meet with staff from CTGR and CTUIR monthly to ensure open communications. # Additionally, for all new land use applications, Planning staff send notification to tribal contacts.

# Status: - Confederated Tribes of the Umatilla Indian Reservation - Staff meet regularly with staff from the Confederated Tribes of the Umatilla to discuss the Cayuse Five Tribute project. The City Commission authorized $150,000 towards completion and staff are continuing to support the delivery of the Cayuse Five Tribute. - City Commissioners and staff met with CTUIR Board of Trustees in July 2023 in support of government-to-government relations. - After this meeting, design work on the Cayuse 5 Tribute was finalized and presentations were made to the Historic Review Board and the Parks and Recreation Advisory Committee. - The Cayuse 5 Memorial project is designed, has reached land use approval, the design was also approved by the HRB and PRAC, bids have been solicited and the project is scheduled to be awarded at the March 20 City Commission Meeting. - The Cayuse Tribute will be completed late spring/early summer 2024 and Staff continues to work with CTUIR Staff on the commemorative event and agreement for long term management of the Tribute. # Confederated Tribes of the Grand Ronde: # Staff meet monthly with staff from the Confederated Tribes of Grand Ronde to identify opportunities to increase communication, explore formalizing a government-to-government relationship, and support private development. - Staff also continue to meet separately with CTGR regarding redevelopment of the Blue Herron site now called Tumwata Village. Staff visited the site in late May to learn more about the redevelopment plans. - Staff and the Consultant Design Team meet separately with the CTGR regarding the McLoughlin Boulevard Enhancement (10th to tumwata village) to discuss the project and the various findings as we move through the study. - The Willamette Falls project team discontinued meetings in March 2022 when it became clear that progress was not being made.